## Sheet1
ShristiJewels
Identified By:Revathy R Nair Reported To: Date:25-12-2022 Version No: Environment Details:MicrosoftEdge,Windows11 Website:https://shrishtijewels.in/
Bugid | ExpectedResult | Bugdescription | StepstoReproduce | Severity | Priority | Screenshot | Status
SJ_SU_01 | Emailid shouldn't have specialcharacters | Emailid have specialcharacters | 1)Open website 2)click on create account 3)enter emailid | Major |  |  | New
SJ_SU_02 | Emailid should be valid | Emailid is not valid | 1)Open website 2)click on create account 3)enter emailid | critical |  |  | New
SJ_SU_03 | Emaild should be in correct format | Emailid is not correct format | 1)Open website 2)click on create account 3)enter emailid | Major |  |  | New
SJ_SU_04 | Password should not be same as username | Password is same as username | 1)Open website 2)click on create account 3)enter password | Major |  |  | New
SJ_SU_05 | PrivacyPolicy page should be workon registeration page | privacypage is not working on registeration page | 1)Open website 2)click on create account 3)click on privacypolicy | Minor |  | https://1drv.ms/u/s!AiTfbxl-6x-jmmw0psj1aIqudcnw | New
SJ_SU_06 | Should terms and conditions are accepted. | terms and condition doesn’t have checkbox for useracceptance. | 1)Open website 2)click on create account 3)look on terms and conditions | Major |  |  | New
SJ_SU_07 | Should have confirmation message on successful signup | confirmationmessage is not sent | 1)Open website 2)click on create account 3)enter username and password 4)click on submit | Major |  |  | New
SJ_SU_08 | should redirect to loginpage after signup | signup not redirecting to loginpage | 1)Open website 2)click on create account 3)enter username and password 4)click on submit | Major |  |  | New
SJ_SU_09 | shouldnot have multipleprivacyand policy content | privacy and policy content is repeated | 1)Open website 2)look on privacy and policy content | Minor |  |  | New
SJ_SU_10 | should have emailid verification | emaildverification is not provided |  | Enhancement |  |  | New
SJ_SU_11 | should have confirmationmessage sent to emailid is registered with | confirmationmessage is not sent |  | Enhancement |  |  | New
SignIn
SJ_SI_01 | shouldn’t autofill the passwordfield | password field is autofilled | 1)Open website 2)click on signin 3)enter username 4)look on password field | Critical |  |  | New
SJ_SI_02 | should receive alert when sigin from unused device or browser | not receiving alert on multipleloginattempts | 1)Open website 2)click on signin 3)enter username 4)enter password | Critical |  |  | New
|  | not receiving loginsuccess message | 1)Open website 2)click on signin 3)enter username 4)enter password | Major |  |  | New
SJ_SI_04 | should resetpassword link receive new password for corresponding mailid | not receiving newpassword | 1)Open website 2)click on signin 3)click on lostpassword | Major |  |  | New
SJ_SI_05 | should sessiontimeout after long duration | page is in idle state |  | Major |  |  | New
SJ_SI_06 | should receive confirmation on successful login | not receive confirmation message | 1)Open website 2)click on login | Minor |  |  | New
SJ_SI_07 | can login with new username and if newpassword is updated | cannot login with new password | 1)Open website 2)click on login | Major |  |  | New
SJ_SI_08 | should autofillthe resetpassword code that is received | there is noautofill of password |  | Enhancement |  |  | New
SJ_SI_09 | should have alternatecontact option for resetpassword | there is no alternate option for reset password |  | Enhacement |  |  | New
Home
SJ_HE_01 | Model image should be fully visible | Modelimage is not fully visible | 1)Open website 2)Look on modelimage | Minor |  | https://drive.google.com/file/d/1Lw2AY0zYHrARyFz9M00-yaq-ijkpTKub/view?usp=share_link | New
SJ_HE_02 | Shopnow button should work | Shopnow button is not working | 1)Open website 2)click on shopnow | Minor |  |  | New
SJ_HE_03 | ReadMore content should have descriptions | Readmore content is not added any desciption | 1)Open website 2)click on readmore content | Minor |  |  | New
SJ_HE_04 | FooterMenus should redirect to approximate pages | FooterMenus are not working | 1)Open website 2)clickon footermenus | Major |  |  | New
SJ_HE_05 | Should specify the need of multiple emailid | two email ids are provided | 1)Open website 2)clickon footermenus | Minor |  |  | New
SJ_HE_06 | Should have chatsupport | no chatsupport is provided |  | Enhancement |  |  | New
SJ_HE_07 | should have zoomin and zoomout option | no zoom in and out option |  | Enhancement |  |  | New
SJ_HE_08 | shouldn’t affect the icon when doubleclick | icon is changing on double click | 1)Open website 2)doubleclick on icons | Major |  |  | New
SJ_HE_09 | searchbar should work | Searchbar is not working | 1)Open website 2)click on searchbar | Major |  |  | New
Collections
SJ_CS_01 | Sort feature should work | Sort feature is not working | 1)open website 2)click on collections | major |  |  | New
SJ_CS_02 | Contents should not repeat | Contents are repeating | 1)open website 2)look on contents | major |  |  | New
SJ_CS_03 | Should specify new arrivals | new arrivals are not specified |  | Enhancement |  |  | New
SJ_CS_04 | some products specified under categories should include items | It displays error message on looking for items | 1)open website 2)click on collections 3)look on items | Major |  |  | New
SJ_OB_01 | Shouldn’t allow to purchase without signin | can purchase products without login | 1)click on website 2)click on collections 3)place an order | Major |  |  | New
SJ_OB_02 | cancel order should be possible | no order can be cancelled | 1)click on website 2)click on collections 3)look on order | Minor |  |  | New
SJ_OB_03 | cod option should add | no cod facility |  | Enhacement |  |  | New
SJ_OB_04 | luckydraw contest should conduct monthly | no luckydraw contest |  | Enhacement |  |  | New
SJ_OB_05 | copypaste the couponcode should possible | no copypaste option |  | Enhacement |  |  | New
SJ_OB_06 | orderconfirmation should sent to verified emailid | no orderconfirmation to emailid | 1)click on website 2)click on cart 3)proceed to checkout 4)pay amount 5)look for orderconfirmationmessage | Minor |  |  | New
SJ_OB_07 | should have deliveryperiod timing | no deliveryperiod specified |  | Minor |  |  | New
SJ_OB_08 | should have defaultaddress option | no defaultaddress field |  | Enhancement |  |  | New
SJ_OB_09 | should have the option to move the deleted prduct from cart to wishlist if they needed | no wishlist option after deletion from cart | 1)click on website 2)click on cart 3)remove from cart | Minor |  | https://drive.google.com/file/d/1WDZzda245n68enn2dx-IhV8I3K_ZVbU7/view?usp=share_link | New
SJ_OB_10 | should have option for gift available | no gift option available |  | Enhanceemnt |  |  | New
SJ_OB_11 | should have orderno displayed with confirmation message | no orderno displayed | 1)click on website 2)click on cart 3)proceed to checkout 4)pay amount 5)look for orderconfirmationmessage have orderid | Enhancement |  |  | New